## Total junction summary (hidden)
Vizag Smart city project junction list
Sl no | Junctions | Scope | Number of junction received | Remark
1 | RLVD junctions | 10 | 10 | Request for final approval to proceed further.
2 | Surveillance Junctions without existing camera | 100 | 66 | As per last meeting , we are proceeding. Request you to kindly review and revert. Also note that we have marked on google earth and shared kmz file.
3 | Surveillance Junctions with existing camera |  | 60 | As per last meeting , updated the list with existing cameras and our proposal. Please review and suggest on balance junctions (34 nos) for further proceedings.
4 | Unidentified Junctions |  | 5 | Location not found
5 | Environmental sensor junction | 15 | 15 | Request for final approval to proceed further.
6 | Bus stop location | 50 | 56 | Awaiting for meeting with Technical team of RTC for further working.
7 | Buses for system integration | 100
8 | Smart Pole | 50 |  | This will be decided after smart pole design submission
9 | Solid waste management | 50 |  | Will be decided after joint meeting with OEM and stakeholder
10 | PA and ECB location | 50 |  | As per todays discussion, Police dept will finalise on 10th july'17
| VMD | 10 |  | As per todays discussion, Police dept will finalise on 10th july'17

## All 131 Surveillance junction (hidden)
Junction List provided by Police department and survey report
S.No | Police Station | Name Of the Junction | L&T Proposed Camera |  | Exisitng camera |  |  | PA | ECB | Reamarks
|  |  | Fixed | PTZ | Fixed | Mini PTZ | PTZ
1 | IV town | Asilametta | 4 | 1 | 0 | 2 | 1
2 | IV town | Dwaraka | 3 | 1 | 0 | 3 | 0
3 | Arilova | Hanumanthuwaka | 4 | 1 | 0 | 0 | 0
4 | III town | MVP Double Road | 4 | 1 | 0 | 0 | 0
5 | III town | Satyam Junction | 4 | 1 | 0 | 2 | 1
6 | IV town | Gurudwara | 3 | 1 | 0 | 2 | 1
7 | Kancharapalem | Tatichetlapalem | 5 | 1 | 0 | 2 | 1
8 | Kancharapalem | NAD | 8 | 2 | 0 | 1 | 1 |  |  | 4 RLVD cameras
9 | Gajuwaka | Old Gajuwaka | 7 | 1 | 0 | 0 | 0
10 | III town | Tycoon | 3 | 1 | 0 | 1 | 0
11 | Kancharapalem | Burma(Urvasi) | 5 | 1 | 0 | 2 | 0 |  |  | Burma Junction,2 RLVD Cameras
12 | Gajuwaka | Sheelanagar | 3 | 1 | 0 | 0 | 0 |  |  | 3 Roads are covered under RLVD System 2 ANPR, 1 Over view
13 | III town | Maddilapalem | 5 | 1 | 0 | 2 | 1
14 | Kancharapalem | Birla | 3 | 1 | 1 | 1 | 1
15 | PM Palem | Carshed | 4 | 1 | 2 | 0 | 0
16 | Gajuwaka | 100 feet Road | 3 | 1 | 2 | 0 | 0
17 | parawada | Lankelapalem | 4 | 1 | 4 | 0 | 0
18 | Steelplant | Kurmanapalem | 4 | 1 | 4 | 0 | 0 |  |  | Seethammadara Circle
19 | IV town | santhipuram | 3 | 1 | 0 | 0 | 0
20 | IV town | Akkayapalem | 4 | 1 | 3 | 0 | 0
21 | III town | Venkojipalem | 3 | 1 | 0 | 0 | 0
22 | Gajuwaka | Autonagar | 5 | 1 | 0 | 0 | 0
23 | Kancharapalem | Airport | 4 | 1 | 0 | 2 | 0
24 | Gajuwaka | BHPV | 6 | 1 | 0 | 0 | 0
25 | Gajuwaka | Srinagar | 4 | 1 | 0 | 0 | 0
26 | III town | Masque | 3 | 1 | 0 | 0 | 0 |  |  | Ramatalkies junction
27 | Kancharapalem | Ramanna Colony | 4 | 1 | 1 | 1 | 1
28 | Pendurthi | Vepagunta | 7 | 2 | 4 | 0 | 0
29 | Gopalapatnam | Gopalapatnam petrol Bunk | 5 | 1 | 0 | 0 | 0
30 | PM Palem | yendada | 3 | 1 | 2 | 0 | 0
31 | Steelplant | Vadlapudi | 3 | 1 | 0 | 0 | 0
32 | Steelplant | Agnampudi Anjaney Swmy temple Junction | 4 | 1 | 3 | 0 | 0 |  |  | Need Junction location clarification
33 | Kancharapalem | Kakani Nagar | 3 | 1 | 3 | 0 | 0
34 | IV town | sangam Sarat | 4 | 2 | 1 | 1 | 0
35 | Pendurthi | Pendurthi | 5 | 1 | 4 | 0 | 0
36 | Arilova | Adarsh Nagar | 4 | 1 | 0 | 0 | 0 |  |  | Dairy Form Junction
37 | III town | Automotive | 3 | 1 | 0 | 2 | 0
38 | II town | Ambedkar Circle | 3 | 1 | 0 | 1 | 1
39 | IV town | Sri Surya | 2 | 1 | 0 | 2 | 0
40 | IV town | ICICI Dwaraka | 3 | 1 | 0 | 0 | 0
41 | IV town | Rail Club(DLO) | 4 | 1 | 0 | 2 | 0
42 | Kancharapalem | kancharapalem Mettu | 4 | 1 | 0 | 0 | 0 |  |  | kapparada junction
43 | Bhimili | Tagarapuvalasa High way point | 5 | 1 | 3 | 0 | 0
44 | Anandapuram | Boyapalem Y | 3 | 1 | 0 | 0 | 0
45 | IV town | Golden jubilee hospital | 4 | 1 | 0 | 0 | 0 |  |  | Highway point
46 | III town | Swarnabharathi Stadium | 3 | 1 | 0 | 1 | 1
47 | Kancharapalem | Punjab hotel | 6 | 2 | 1 | 1 | 1
48 | Kancharapalem | R&B | 5 | 1 | 1 | 1 | 1
49 | II town | Sevenhills | 4 | 1 | 0 | 0 | 1
50 | III town | rama talkies | 5 | 1 | 0 | 1 | 1
51 | II town | Gollapalem Junction | 4 | 1 | 0 | 4 | 1
52 | II town | Watch house | 3 | 1 | 0 | 1 | 1
53 | II town | CPO | 3 | 1 | 0 | 2 | 1
54 | Pendurthi | Gosala | 6 | 1 | 0 | 0 | 0
55 | Gopalapatnam | Gopalapatnam RS | 4 | 1 | 0 | 0 | 0
56 | IV town | ASR Statue | 5 | 1 | 0 | 0 | 0 |  |  | Seethammadara Circle
57 | I town | Collectorate | 6 | 1 | 0 | 0 | 0
58 | II town | Pen School | 4 | 1 | 0 | 2 | 0
59 | II town | Haritha Lodge | 3 | 1 | 1 | 2 | 0
60 | I town | Town kotha Road | 4 | 1 | 0 | 0 | 0 |  |  | No provision for the CCTV Pole
61 | II town | Tenneti | 2 | 1 | 0 | 0 | 1
62 | Harbour | Convent | 4 | 1 | 0 | 0 | 0
63 | Harbour | Essar | 4 | 1 | 0 | 0 | 0
64 | Harbour | Y-Jn-Gosthani park | 3 | 2 | 0 | 0 | 0
65 | III town | Patel junction | 5 | 2 | 0 | 0 | 1
66 | I town | Coastal Battery | 3 | 1 | 0 | 1 | 1
67 | I town | Durgalamma temple | 4 | 1 | 0 | 2 | 0
68 | Kancharapalem | kapparada | 4 | 1 | 0 | 0 | 0
69 | I town | Sea Horse | 4 | 1 | 0 | 2 | 0
70 | III town | N.T.R.circle Beach | 3 | 1 | 0 | 3 | 0
71 | II town | Turner choultry | 3 | 1 | 0 | 2 | 1
72 | II town | saraswathi | 6 | 2 | 0 | 2 | 0
73 | II town | Ramakrishna | 3 | 1 | 0 | 2 | 0
74 | II town | Dolphin | 4 | 1 | 0 | 2 | 0
75 | Bhimili | Tagarapuvalasa Old Bus stand | 4 | 1 | 3 | 0 | 0
76 | II town | Pandimetta | 4 | 1 | 0 | 0 | 0
77 | II town | GVMC Gandhi Statue | 7 | 2 | 0 | 2 | 1
78 | II town | Novotel Hotel Down | 3 | 1 | 0 | 2 | 1
79 | II town | Z.P. | 4 | 1 | 0 | 2 | 0
80 | II town | Jagadamba | 4 | 1 | 0 | 1 | 1
81 | III town | Circuit House | 4 | 1 | 0 | 1 | 0
82 | III town | Siripuram | 7 | 2 | 0 | 0 | 1
83 | III town | Appughar | 3 | 1 | 0 | 0 | 0
84 | III town | Park hotel | 6 | 1 | 0 | 1 | 2
85 | III town | Pedawaltair | 4 | 1 | 0 | 0 | 0
86 | III town | All India Radio | 7 | 2 | 0 | 1 | 1
87 | III town | CMR Engineering College | [7 empty] | Location not found
88 | III town | Pandurangapuram down | 3 | 1 | 0 | 1 | 1
89 | III town | CR Reddy Square | 4 | 1 | 0 | 4 | 0
90 | III town | YMCA | 3 | 1 | 0 | 0 | 0
91 | III town | Pandurangapuram temple | 4 | 1 | 0 | 0 | 0
92 | III town | Pithapuram colony | 3 | 1 | 0 | 0 | 0
93 | IV town | Dondaparthy | 4 | 1 | 1 | 1 | 0
94 | IV town | Railway new colony | 4 | 2 | 1 | 2 | 0
95 | IV town | Maharani Parlour | 3 | 1 | 1 | 1 | 0
96 | IV town | Railway High School Raod junction | 4 | 1 | 0 | 2 | 0
97 | IV town | Diamond park | 4 | 2 | 0 | 0 | 0
98 | Pendurthi | Pinagadi | 4 | 1 | 0 | 0 | 0
99 | Pendurthi | Sujataha Nagar | 5 | 1 | 0 | 0 | 0
100 | Pendurthi | Chinna musidiwada | 6 | 1 | 0 | 0 | 0
101 | Anandapuram | Totagaruvu | 3 | 1 | 0 | 0 | 0 |  |  | Sri chaitanya point
102 | Malkapuram | Maruthi Circle | 5 | 1 | 0 | 0 | 0
103 | Malkapuram | Pipe Line Junction | 3 | 1 | 0 | 0 | 0
104 | Malkapuram | Coromandel Gate | 3 | 1 | 0 | 0 | 0
105 | Malkapuram | Scindia | 3 | 1 | 0 | 0 | 0
106 | II town | Gokul theater junction | 3 | 1 | 0 | 0 | 0
107 | Kancharapalem | Muralinagar | 5 | 1 | 1 | 1 | 1 |  |  | Birla juncton
108 | Kancharapalem | NAD Colony (Blinker)
109 | Gajuwaka | Natayyapalem | 4 | 1 | 0 | 0 | 0
110 | Gajuwaka | New Gajuwaka
111 | Gajuwaka | Old traffic P.S | 3 | 1 | 0 | 0 | 0 |  |  | Taken reference as mangalagiri complex ,with the inputs from C.I.
112 | New port | Venkanna palem Port Junction | 3 | 1 | 0 | 0 | 0 |  |  | Need Junction location clarification
113 | New port | karnavanipalem Junction | 3 | 1 | 0 | 0 | 0
114 | New port | gangavaram port junction | 4 | 1 | 0 | 0 | 0
115 | PM Palem | Rushikonda | 3 | 1 | 2 | 0 | 0
116 | Arilova | Sagar Nagar | 3 | 1 | 1 | 0 | 0
117 | Arilova | Visalakshi nagar N116 | 3 | 1 | 0 | 0 | 0 |  |  | SBI T-Point
118 | Arilova | Visalakshi nagar Beach Road | 3 | 1 | 0 | 0 | 0
119 | Arilova | Jodugullapalem | 3 | 1 | 0 | 0 | 0 |  |  | Nex to tenneti park point to wards left kailsagiri
120 | Arilova | kailsagiri /Hanumanthwaka /BRTS Colony | 3 | 1 | 0 | 0 | 0 |  |  | T -Point -at Hanumanthuwaka
121 | Arilova | East point golf junction-Blinker | 6 | 1 | 0 | 0 | 0 |  |  | As per S.I.Suresh suggestions point taken as Denidayalpuram
122 | Arilova | Mudasarlova Rear side | [7 empty] | Location not found
123 | PM Palem | Cricket Stadium Junction | 3 | 1 | 0 | 0 | 0
124 | PM Palem | Madhurawada | 4 | 1 | 0 | 0 | 0
125 | Arilova | Krishnapuram C Jail Junction | 5 | 1 | 0 | 0 | 0
126 | Arilova | Doratota | [7 empty] | Location not found We have Dora palem
127 | I Town | Fishing harbour Blinker | 3 | 1 | 0 | 0 | 0 |  |  | Need area clarity
128 | I Town | Old Post office Blinker | 5 | 2 | 0 | 0 | 0 |  |  | Scattered and critical point
129 | I Town | Victoria Statue Blinker | 5 | 2 | 0 | 0 | 0
130 | IV Town | Railway Station Out gate-Blinker | 2 | 1 | 0 | 0 | 0
131 | IV Town | Railway Station In gate-Blinker | 2 | 1 | 0 | 0 | 0
|  |  | 501 | 140
Note-: L&T proposed cameras qty may changes based on the client approval

## BANDWIDTH_SUMMARY
S. No. | Description |  | Bandwidth in Mbps | Link Requirement | Comment
1 | Bandwidth for 115 junctions ( CCTV SURVEILLANCE , RLVD , PAS , ECB , SIGNALLING) |  | 4463 | 1 Gbps/ 100 Mbps Single Mode Fibre link at each location (Refer the list of Junctions for more details) - 34 Junctions locations mentioned in the list - Row no. 71 onwards for CCTV surveilance needs confirmation | The link should be in ring or redundant connectivity
2 | Bandwidth for 50 smart pole locations |  | 1020 | 1 Gbps Single Mode Fibre Link at each location | The link should be in ring or redundant connectivity
3 | Bandwidth for 423 existing cameras |  | 2538 |  | feed from the existing Police CCC
4 | bandwidth for bus stops - 50 Nos. |  | 300 | 100 Mbps Single Mode Fibre Link at each location | The link should be in ring or redundant connectivity
5 | Bandwidth for bus stations - 5 nos. |  | 150 | 100 Mbps Single Mode Fibre Link at each location | The link should be in ring or redundant connectivity
6 | Bandwidth for VMD - 10 nos. |  | 50 | 100 Mbps Single Mode Fibre Link at each location | The link should be in ring or redundant connectivity
7 | Bandwidth for Primary CCC |  | 0 |  | May not be required if feed is taken from DC L3 switch to the CCC
8 | Bandwidth for DC |  | 8521 | 2 nos. of 2x10Gbps Single Mode Fibre Link
9 | Bandwidth for DC-DR on Dark Fiber |  | 2x10G | 2x10 Gbps Single Mode Fibre Link
10 | Bandwidth for secondary CCC |  | 7151 | 2*10 Gbps Single Mode Fibre Link
Expectations from Network Service Provider:
1 | Service provider network should support Multicast (PIM, IGMP).
2 | Any to any MPLS connectivity should be established for end to end reachability.
3 | Junction aggregation point for edge devices should be service provider switch at POP i.e. gateway for all junction edge devices should be POP aggregation switch.
4 | 2x10G Dark fiber redundant connectivity with different paths should be provided across two datacenters.
5 | Redundancy links and redundant paths from the NSP to be provided at Datacenter and CCC.
6 | Location of the NSP POPs to be identified jointly with respect to the junctions.
Requirement from Internet Service Provider
1 | Internet leased line connectivity of 1.25 Gbps at DC (considering 1.02Gbps for Smart Poles and 0.23 Gbps for applications at Data Center) and 10Mbps at DR with 1.25Gbps failover connectivity at DR
| X coordinate | Y coordinate
Data Centre/PCCC/GVMC office | 83.3085 | 17.723
SCCC/ CP office( control room) | 83.2994 | 17.7102

## JUNCTIONS
Visakhapatnam Smart City
System Integrator Project - CCTV RLVD Locations
Sl no | Police Station | Name Of the Junction | [5 empty] | CCTV
|  |  | X Coordinate | Y Coordinates | RLVD junctions | OV | ANPR/LPU | fixed=404 | PTZ=99 |  |  | PAS=42 |  |  | ECB=40 | Signalling | BW in Each Locn ( Mbps) | LINK Provisioing for each JB | Number of Links at Junction
|  | BANDWIDTH (Mbps) / DEVICE |  |  |  | 20 | 5 | 5 | 7 |  |  | 5 |  |  | 5 | 2
1 | Arilova | Hanumanthuwaka | 83.3324 | 17.7549 | RLVD junction | 4 | 16 | 10 | 2 | Hanumanthuwaka | 1 | 1 | #N/A | #N/A | 0 | 1 | 231 | 1GB | 2
2 | MVP | MVP Double Road | 83.3279 | 17.7428 | RLVD junction | 4 | 11 | 6 | 1 | MVP Double Road | 1 | 1 | #N/A | #N/A | 0 | 1 | 179 | 1GB | 2
3 | Gajuwaka | Old Gajuwaka | 83.2036 | 17.6851 | RLVD junction | 4 | 12 | 11 | 2 | Old Gajuwaka | 1 | 1 | Old Gajuwaka | 1 | 1 | 1 | 221 | 1GB | 2
4 | Gajuwaka | Sheelanagar | 83.2037 | 17.7195 |  |  |  | 6 | 1 | Sheelanagar | 1 | 1 | Sheelanagar | 1 | 1 | 1 | 49 | 1GB | 1
5 | IV town | santhipuram | 83.3048 | 17.7378 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 | 1 | 34 | 100MB | 1
6 | MVP | Venkojipalem | 83.3311 | 17.7475 |  |  |  | 3 | 1 | Venkojipalem | 1 | 1 | #N/A | #N/A | 0 | 1 | 29 | 100MB | 1
7 | Gajuwaka | Autonagar | 83.2053 | 17.6973 | RLVD junction | 3 | 9 | 7 | 1 | Autonagar | 1 | 1 | #N/A | #N/A | 0 | 1 | 154 | 1GB | 2
8 | Gajuwaka | BHPV | 83.2056 | 17.7019 |  |  |  | 8 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 | 1 | 49 | 1GB | 1
9 | Gajuwaka | Srinagar | 83.1884 | 17.6836 |  |  |  | 4 | 1 | Srinagar | 1 | 1 | #N/A | #N/A | 0 | 1 | 34 | 100MB | 1
10 | III town | Masque | 83.3141 | 17.7296 |  |  |  | 5 | 1 | Masque | 1 | 1 | #N/A | #N/A | 0 | 1 | 39 | 100MB | 1
11 | Gopalapatnam | Gopalapatnam petrol Bunk | 83.2178 | 17.7517 |  |  |  | 5 | 1 | Gopalapatnam petrol Bunk | 1 | 1 | #N/A | #N/A | 0 | 1 | 39 | 100MB | 1
12 | Duvvada | Vadlapudi | 83.1705 | 17.6853 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 | 1 | 24 | 100MB | 1
13 | Arilova | Adarsh Nagar | 83.3339 | 17.761 |  |  |  | 5 | 1 | Adarsh Nagar | 1 | 1 | #N/A | #N/A | 0 | 1 | 39 | 100MB | 1
14 | Dwaraka PS | ICICI Dwaraka | 83.3063 | 17.7266 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 1 | 1 | 29 | 100MB | 1
15 | Kancharapalem | kancharapalem Mettu | 83.2784 | 17.7321 |  |  |  | 5 | 1 | kancharapalem Mettu | 1 | 1 | kancharapalem Mettu | 1 | 1 |  | 42 | 1GB | 1
16 | Anandapuram | Boyapalem Junction | 83.3687 | 17.8697 |  |  |  | 7 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 42 | 1GB | 1
17 | IV town | Golden jubilee hospital | 83.2945 | 17.739 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
18 | Gopalapatnam | Gosala | 83.2359 | 17.7711 |  |  |  | 6 | 2 | Gosala | 1 | 1 | #N/A | #N/A | 0 |  | 49 | 1GB | 1
19 | Gopalapatnam | Gopalapatnam RS | 83.2216 | 17.7466 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 32 | 100MB | 1
20 | Dwaraka PS | ASR Statue | 83.3144 | 17.7434 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | ASR Statue | 1 | 1 |  | 32 | 100MB | 1
21 | MR Pet | Collectorate(KGH ) | 83.3079 | 17.7083 |  |  |  | 6 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 37 | 100MB | 1
22 | I town | Town kotha Road | 83.2964 | 17.702 |  |  |  | 4 | 1 | Town kotha Road | 1 | 1 | #N/A | #N/A | 0 |  | 32 | 100MB | 1
23 | Harbour | Convent Jn | 83.2896 | 17.7171 |  |  |  | 8 | 2 | Convent Jn | 1 | 1 | #N/A | #N/A | 1 |  | 64 | 1GB | 1
24 | Harbour | Essar Jn | 83.2816 | 17.7161 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
25 | Harbour | Y Jn Gosthani park | 83.2651 | 17.7142 |  |  |  | 3 | 2 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 29 | 100MB | 1
26 | Kancharapalem | kapparada Jn | 83.2788 | 17.7354 |  |  |  | 8 | 2 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 54 | 1GB | 1
27 | MR Pet | Pandimetta | 83.3125 | 17.7145 |  |  |  | 4 | 1 | Pandimetta | 1 | 1 | Pandimetta | 1 | 1 |  | 37 | 100MB | 1
28 | MVP | Appughar | 83.3436 | 17.7418 |  |  |  | 3 | 1 | Appughar | 1 | 1 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
29 | MVP | Pedawaltair | 83.3353 | 17.7308 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | Pedawaltair | 1 | 1 |  | 32 | 100MB | 1
30 | III town | YMCA | 83.3339 | 17.7193 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 22 | 100MB | 1
31 | III town | Pandurangapuram Junction | 83.322 | 17.7148 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
32 | MVP | Pithapuram colony | 83.3219 | 17.7368 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 22 | 100MB | 1
33 | IV town | Diamond park | 83.3035 | 17.7269 |  |  |  | 6 | 2 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 44 | 1GB | 1
34 | Pendurthi | Pinagadi | 83.1695 | 17.8113 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | Pinagadi | 1 | 1 |  | 32 | 100MB | 1
35 | Pendurthi | Sujataha Nagar | 83.2107 | 17.7987 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 32 | 100MB | 1
36 | Pendurthi | Chinna musidiwada | 83.2089 | 17.8055 |  |  |  | 6 | 1 | #N/A | #N/A | 0 | Chinna musidiwada | 1 | 1 |  | 42 | 1GB | 1
37 | Arilova | Totagaruvu | 83.3761 | 17.8822 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 32 | 100MB | 1
38 | Malkapuram | Maruthi Circle | 83.2323 | 17.7095 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | Maruthi Circle | 1 | 1 |  | 37 | 100MB | 1
39 | Malkapuram | Pipe Line Junction | 83.2696 | 17.6974 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
40 | Malkapuram | Coromandel Gate | 83.2383 | 17.6897 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 22 | 100MB | 1
41 | Malkapuram | Scindia | 83.2685 | 17.6882 |  |  |  | 3 | 1 | Scindia | 1 | 1 | Scindia | 1 | 1 |  | 32 | 100MB | 1
42 | II town | Gokul theater junction | 83.2934 | 17.7173 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | Gokul theater junction | 1 | 1 |  | 27 | 100MB | 1
43 | Gajuwaka | Natayyapalem | 83.2056 | 17.7062 |  |  |  | 7 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 42 | 1GB | 1
44 | Gajuwaka | Old traffic P.S (New Gajuwaka) | 83.2123 | 17.6856 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 22 | 100MB | 1
45 | New port | Venkanna palem Port Junction | 82.9743 | 17.7949 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 22 | 100MB | 1
46 | New port | karnavanipalem Junction | 83.1945 | 17.6778 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 32 | 100MB | 1
47 | New port | gangavaram port junction | 83.2007 | 17.6595 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | gangavaram port junction | 1 | 1 |  | 37 | 100MB | 1
48 | Arilova | Hanumanthwaka Jn (Near Mekala Jn) | 83.3324 | 17.7539 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
49 | Arilova | Visalakshi nagar NH16 | 83.3333 | 17.758 |  |  |  | 4 | 2 | #N/A | #N/A | 0 | Visalakshi nagar NH16 | 1 | 1 |  | 39 | 100MB | 1
50 | Arilova | Visalakshi nagar Beach Road | 83.3508 | 17.7538 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 22 | 100MB | 1
51 | Arilova | Jodugullapalem | 83.3488 | 17.7502 |  |  |  | 3 | 1 | Jodugullapalem | 1 | 1 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
52 | Arilova | East point golf junction | 83.3051 | 17.7622 |  |  |  | 8 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 47 | 1GB | 1
53 | PM Palem | Cricket Stadium Junction | 83.3534 | 17.7965 |  |  |  | 5 | 1 | Cricket Stadium Junction | 1 | 1 | #N/A | #N/A | 0 |  | 37 | 100MB | 1
54 | PM Palem | Madhurawada ( Kommadi Junction ) | 83.3571 | 17.8186 |  |  |  | 6 | 1 | Madhurawada ( Kommadi Junction ) | 1 | 1 | Madhurawada ( Kommadi Junction ) | 1 | 1 | 1 | 49 | 1GB | 1
55 | Arilova | Krishnapuram C Jail Junction | 83.2829 | 17.7691 |  |  |  | 9 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 52 | 1GB | 1
56 | I Town | Fishing harbour Entrance | 83.2995 | 17.6978 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 1 |  | 27 | 100MB | 1
57 | I Town | Old Post office Junction | 83.2922 | 17.6936 |  |  |  | 4 | 2 | #N/A | #N/A | 1 | #N/A | #N/A | 1 |  | 44 | 1GB | 1
58 | I Town | Victoria Statue Junction | 83.2926 | 17.6954 |  |  |  | 5 | 2 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 39 | 100MB | 1
59 | IV Town | Railway Station Out gate | 83.291 | 17.7227 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 1 |  | 27 | 100MB | 1
60 | IV Town | Railway Station In gate Junction | 83.2915 | 17.721 |  |  |  | 3 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 22 | 100MB | 1
61 | Dwaraka | Satyam Junction | 83.313 | 17.7343 | RLVD junction | 4 | 12 | 9 | 1 | Satyam Junction | 1 | 1 | #N/A | #N/A | 0 | 1 | 199 | 1GB | 2
62 | Kancharapalem | Tatichetlapalem | 83.2874 | 17.735 | RLVD junction | 3 | 9 | 7 | 1 | Tatichetlapalem | 1 | 1 | Tatichetlapalem | 1 | 1 | 1 | 159 | 1GB | 2
63 | Airport | NAD | 83.2355 | 17.7427 | RLVD junction | 4 | 12 | 10 | 2 | NAD | 1 | 1 | NAD | 1 | 1 |  | 214 | 1GB | 2
64 | Duvvada | Kurmanapalem | 83.1674 | 17.6851 | RLVD junction | 3 | 9 | 6 | 2 | Kurmanapalem | 1 | 1 | #N/A | #N/A | 0 | 1 | 156 | 1GB | 2
65 | Airport | Muralinagar | 83.26 | 17.7433 | RLVD junction | 2 | 6 | 7 | 1 | #N/A | #N/A | 0 | Muralinagar | 1 | 1 | 1 | 119 | 1GB | 2
66 | Dwaraka PS | Car Shed Junction |  |  | RLVD junction | 4 | 12 | 7 | 2 | #N/A | #N/A | 1 | #N/A | #N/A | 0 | 1 | 196 | 1GB | 2
67 | III town | Park hotel | 83.3356 | 17.7218 |  |  |  | 4 | 1 | Park hotel | 1 | 1 | Park hotel | 1 | 1 |  | 37 | 100MB | 1
68 | Maharani peta | jagdamba | 83.3023 | 17.7119 |  |  |  | 4 | 2 | #N/A | #N/A | 0 | jagdamba | 1 | 1 |  | 39 | 100MB | 1
69 | II town | seven hills | 83.3094 | 17.7178 |  |  |  | 5 | 1 | #N/A | #N/A | 0 | seven hills | 1 | 1 | 1 | 39 | 100MB | 1
70 | III town | Siripuram HSBC Junction | 83.3178 | 17.723 |  |  |  | 4 | 2 | #N/A | #N/A | 1 | #N/A | #N/A | 0 |  | 39 | 100MB | 1
71 | III town | Siripuram-2(CR Reddy square) | 83.3201 | 17.7211 |  |  |  | 4 | 2 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 34 | 100MB | 1
72 | MVP | kurupam circle | 83.3402 | 17.7302 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
73 | III town | N.T.R.circle | 83.3181 | 17.7115 |  |  |  | 5 | 2 | N.T.R.circle | 1 | 1 | N.T.R.circle | 1 | 1 |  | 49 | 1GB | 1
74 | Maharani peta | Z.P junction | 83.311 | 17.7104 |  |  |  | 4 | 1 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 27 | 100MB | 1
75 | III town | Asilametta | 83.3085 | 17.7244 |  |  |  | 5 | 1 | Asilametta | 1 | 1 | #N/A | #N/A | 0 | 1 | 39 | 100MB | 1
76 | III town | Tycoon | 83.3169 | 17.725 |  |  |  | 3 | 1 | Tycoon | 1 | 1 | #N/A | #N/A | 0 | 1 | 29 | 100MB | 1
77 | Dwaraka | Gurudwara | 83.3077 | 17.7367 |  |  |  | 6 | 1 | Gurudwara | 1 | 1 | #N/A | #N/A | 0 | 1 | 44 | 1GB | 1
78 | II town | Dolphin Junction | 83.2973 | 17.7125 |  |  |  | 4 | 2 | #N/A | #N/A | 0 | #N/A | #N/A | 0 |  | 34 | 100MB | 1
79 | II town | I. Gandhi (Gollalapalem) | 83.3063 | 17.7199 |  |  |  | 5 | 1 | #N/A | #N/A | 1 | #N/A | #N/A | 1 | 1 | 44 | 1GB | 1
80 | II town | Ambedkar Circle | 83.3033 | 17.7212 |  |  |  | 8 | 2 | Ambedkar Circle | 1 | 1 | Ambedkar Circle | 1 | 1 | 1 | 66 | 1GB | 1
[5 empty] | 10 |  |  | 404 | 99 | [7 empty] | 2713
|  | PAS&ECB(3) | [14 empty] | 0 |  | 1
81 |  | Agnampudi Anjaney Swmy temple Junction | 83.138 | 17.6896 | [7 empty] | 1 |  |  | 1 |  | 10 | 100MB | 1
82 |  | Durgalamma temple | 83.297 | 17.7077 | [7 empty] | 1 |  |  | 1 |  | 10 | 100MB | 1
83 |  | GVMC Gandhi Statue | 83.3078 | 17.7226 | [7 empty] | 1 |  |  | 1 |  | 10 | 100MB | 1
|  | PA(5) | [14 empty] | 0
84 |  | Burma(Urvasi) | 83.2711 | 17.7369 | [7 empty] | 1 |  |  | 0 | 1 | 7 | 100MB | 1
85 |  | Akkayapalem | 83.3 | 17.7407 | [7 empty] | 1 |  |  | 0 | 1 | 7 | 100MB | 1
86 |  | Airport | 83.2235 | 17.7322 | [7 empty] | 1 |  |  | 0 | 1 | 7 | 100MB | 1
87 |  | Tenneti | 83.303 | 17.712368, | [7 empty] | 1 |  |  | 0 | 1 | 7 | 100MB | 1
88 |  | Gnanapuram | 83.2896 | 17.7171 | [7 empty] | 1 |  |  | 0 |  | 5 | 100MB | 1
|  | ECB(10) | [14 empty] | 0
89 |  | Lankelapalem | 83.0967 | 17.6879 | [7 empty] | 0 |  |  | 1 | 1 | 7 | 100MB | 1
90 |  | Tagarapuvalasa High way point | 83.424 | 17.9287 | [7 empty] | 0 |  |  | 1 |  | 5 | 100MB | 1
91 |  | Swarnabharathi Stadium | 83.3154 | 17.7304 | [7 empty] | 0 |  |  | 1 |  | 5 | 100MB | 1
92 |  | Pen School | 83.3018 | 17.7151 | [7 empty] | 0 |  |  | 1 |  | 5 | 100MB | 1
93 |  | Patel junction | 83.316 | 17.7213 | [7 empty] | 0 |  |  | 1 | 1 | 7 | 100MB | 1
94 |  | Tagrapuvalasa Old Bus Stand | 83.4267 | 17.9324 | [7 empty] | 0 |  |  | 1 |  | 5 | 100MB | 1
95 |  | Dondaparthy | 83.2993 | 17.7272 | [7 empty] | 0 |  |  | 1 |  | 5 | 100MB | 1
96 |  | Maharani Parlour | 83.2999 | 17.7353 | [7 empty] | 0 |  |  | 1 |  | 5 | 100MB | 1
97 |  | Sagar nagar | 83.358 | 17.7667 | [7 empty] | 0 |  |  | 1 |  | 5 | 100MB | 1
98 |  | Krishna College Jn. | Survey to be done for signalling points | [12 empty] | 1 | 2 | 100MB | 1
99 |  | R&B(Ramanna Colony Jn | [13 empty] | 1 | 2 | 100MB | 1
100 |  | Kakani Nagar Jn | [13 empty] | 1 | 2 | 100MB | 1
101 |  | 100 feet road Jn. | [13 empty] | 1 | 2 | 100MB | 1
102 |  | Dwarakanagar Jn. | [13 empty] | 1 | 2 | 100MB | 1
103 |  | Sangam Sarat Jn. | [13 empty] | 1 | 2 | 100MB | 1
104 |  | Rail Club(DLO Jn.) | [13 empty] | 1 | 2 | 100MB | 1
105 |  | 28 Bus stop(TC palem BNITN Colony) Jn. | [13 empty] | 1 | 2 | 100MB | 1
106 |  | Sri Surya Jn. | [13 empty] | 1 | 2 | 100MB | 1
107 |  | CPO Jn. | [13 empty] | 1 | 2 | 100MB | 1
108 |  | Watch House Jn. | [13 empty] | 1 | 2 | 100MB | 1
109 |  | Pedagadili Jn. | [13 empty] | 1 | 2 | 100MB | 1
110 |  | Chinagadili Jn. | [13 empty] | 1 | 2 | 100MB | 1
111 |  | Maddilapalem | [13 empty] | 1 | 2 | 100MB | 1
112 |  | Vepagunta | [13 empty] | 1 | 2 | 100MB | 1
113 |  | yendada | [13 empty] | 1 | 2 | 100MB | 1
114 |  | Pendurthi | [13 empty] | 1 | 2 | 100MB | 1
115 |  | rama talkies | [13 empty] | 1 | 2 | 100MB | 1
4463

## GVSCCL-PAS FINAL LIST (hidden)
Visakhapatnam Smart City
System Integrator Project - PAS Locations
Sl no | Police Station | Name Of the Junction | PAS |  |  | NOW | NOW
1 | Arilova | Hanumanthuwaka | 1 | Hanumanthuwaka | Hanumanthuwaka | Hanumanthuwaka | Hanumanthuwaka
2 | MVP | MVP Double Road | 1 | MVP Double Road |  | MVP Double Road | MVP Double Road | Hanumanthuwaka
3 | Gajuwaka | Old Gajuwaka | 1 | Old Gajuwaka | Old Gajuwaka | Old Gajuwaka | Old Gajuwaka | MVP Double Road
4 | Gajuwaka | Sheelanagar | 1 | Sheelanagar | Sheelanagar | Sheelanagar | Sheelanagar | Old Gajuwaka
5 | MVP | Venkojipalem | 1 | santhipuram | Venkojipalem | Venkojipalem | Venkojipalem | Sheelanagar
6 | Gajuwaka | Autonagar | 1 | Venkojipalem | Autonagar | Autonagar | Autonagar | Venkojipalem
7 | Gajuwaka | Srinagar | 1 | Autonagar | Srinagar | Srinagar | Srinagar | Autonagar
8 | III town | Masque | 1 | BHPV | Masque | Masque | Masque | Srinagar
9 | Gopalapatnam | Gopalapatnam petrol Bunk | 1 | Srinagar | Gopalapatnam petrol Bunk | Gopalapatnam petrol Bunk | Gopalapatnam petrol Bunk | Masque
10 | Arilova | Adarsh Nagar | 1 | Masque | Adarsh Nagar | Adarsh Nagar | Adarsh Nagar | Gopalapatnam petrol Bunk
11 | Kancharapalem | kancharapalem Mettu | 1 | Gopalapatnam petrol Bunk | kancharapalem Mettu | kancharapalem Mettu | kancharapalem Mettu | Adarsh Nagar
12 | Gopalapatnam | Gosala | 1 | Vadlapudi | Gosala | Gosala | Gosala | kancharapalem Mettu
13 | MR Peta | Collectorate | 1 | Adarsh Nagar | Collectorate | Collectorate | Collectorate | Gosala
14 | I town | Town kotha Road | 1 | ICICI Dwaraka | Town kotha Road | Town kotha Road | Town kotha Road | Collectorate
15 | Harbour | Convent Jn | 1 | kancharapalem Mettu | Convent Jn | Convent Jn | Convent Jn | Town kotha Road
16 | II town | Pandimetta | 1 | Boyapalem Jn | Pandimetta | Pandimetta | Pandimetta | Convent Jn
17 | III town | Appughar | 1 | Golden jubilee hospital | Appughar | Appughar | Appughar | Pandimetta
18 | Malkapuram | Scindia | 1 | Gosala | Scindia | Scindia | Scindia | Appughar
19 | Arilova | Jodugullapalem | 1 | Gopalapatnam RS Jn | New Gajuwaka | Jodugullapalem | Jodugullapalem | Scindia
20 | PM Palem | Cricket Stadium Junction | 1 | ASR Statue | Jodugullapalem | Cricket Stadium Junction | Cricket Stadium Junction | New Gajuwaka
21 | PM Palem | Madhurawada ( Kommadi Junction ) | 1 | Collectorate | Cricket Stadium Junction | Madhurawada ( Kommadi Junction ) | Madhurawada ( Kommadi Junction ) | Jodugullapalem
22 | I Town | Old Post office | 1 | Town kotha Road | Madhurawada ( Kommadi Junction ) | #N/A | 0 | Cricket Stadium Junction
23 | IV Town | Railway Station In gate | 1 | Convent Jn | Railway Station In gate | Railway Station In gate | Railway Station In gate | Madhurawada ( Kommadi Junction )
24 | Dwaraka | Satyam Junction | 1 | Essar Jn | Satyam Junction | Satyam Junction | Satyam Junction | Railway Station In gate
25 | Kancharapalem | Tatichetlapalem | 1 | Y-Junction | Tatichetlapalem | Tatichetlapalem | Tatichetlapalem | Satyam Junction
26 | Airport | NAD | 1 | kapparada Jn | NAD | NAD | NAD | Tatichetlapalem
27 | Duvvada | Kurmanapalem | 1 | Pandimetta | Kurmanapalem | Kurmanapalem | Kurmanapalem | NAD
28 | Dwaraka | RTC X Roads( near TSR) | 1 | Appughar | Park hotel | #N/A | 0 | Kurmanapalem
29 | III town | Park hotel | 1 | Pedawaltair | N.T.R.circle | Park hotel | Park hotel | Park hotel
30 | III town | N.T.R.circle | 1 | YMCA | Asilametta | N.T.R.circle | N.T.R.circle | N.T.R.circle
31 | IV town | Asilametta | 1 | Pandurangapuram Jn | Tycoon | Asilametta | Asilametta | Asilametta
32 | III town | Tycoon | 1 | Pithapuram colony | Gurudwara | Tycoon | Tycoon | Tycoon
33 | Dwaraka | Gurudwara | 1 | Diamond park | Ambedkar Circle | Gurudwara | Gurudwara | Gurudwara
34 | II town | Ambedkar Circle | 1 | Pinagadi | Ambedkar Circle | Ambedkar Circle | Ambedkar Circle | Ambedkar Circle
35 | IV town | Dwaraka | 1 | Sujataha Nagar | #N/A | #N/A | 0
36 | Kancharapalem | Burma(Urvasi) | 1 | Chinna musidiwada | #N/A | #N/A | 0
37 | III town | Maddilapalem | 1 | Totagaruvu | #N/A | #N/A | 0
38 | IV town | Akkayapalem | 1 | Maruthi Circle | #N/A | #N/A | 0
39 | Airport | Airport | 1 | Pipe Line Junction | #N/A | #N/A | 0
40 | Pendurthi | Vepagunta | 1 | Coromandel Gate | #N/A | #N/A | 0
41 | PM Palem | yendada | 1 | Scindia | #N/A | #N/A | 0
42 | Steelplant | Agnampudi Anjaney Swmy temple Junction | 1 | Gokul theater junction | #N/A | #N/A | 0
43 | Pendurthi | Pendurthi | 1 | Natayyapalem | #N/A | #N/A | 0
44 | III town | rama talkies | 1 | New Gajuwaka | #N/A | #N/A | 0
45 | II town | Gollapalem Junction | 1 | Venkanna palem Port Junction | #N/A | #N/A | 0
46 | II town | Tenneti | 1 | karnavanipalem Junction | #N/A | #N/A | 0
47 | I town | Durgalamma temple | 1 | gangavaram port junction | #N/A | #N/A | 0
48 | II town | GVMC Gandhi Statue | 1 | Hanumanthwaka Jn (Near Mekala Jn) | #N/A | #N/A | 0
49 | Gajuwaka | New Gajuwaka | 1 | Visalakshi nagar NH16 | New Gajuwaka | New Gajuwaka | New Gajuwaka
50 | Kancharapalem | Gnanapuram | 1 | Visalakshi nagar Beach Road | #N/A | #N/A | 0
|  |  | 50 | Jodugullapalem
East point golf junction
Cricket Stadium Junction
Madhurawada ( Kommadi Junction )
Krishnapuram C Jail Junction
Fishing harbour Entrance
Old Post office Jn
Victoria Statue Jn
Railway Station Out gate
Railway Station In gate
Satyam Junction
Tatichetlapalem
NAD
Kurmanapalem
Muralinagar
Dwaraka Jn
Park hotel
jagdamba
seven hills
Siripuram HSBC Junction
C.R Reddy Jn
kurupam circle
N.T.R.circle
Z.P
Asilametta
Tycoon
Gurudwara
dolphin/sea nose
Gollapalem Statue
Ambedkar Circle

## Sheet2 (hidden)
PAS | ECB | PAS&ECB |  | PA | ECB
Old Post office | Convent | #N/A | 0 | Old Post office | Convent | #N/A | 0
RTC X Roads( near TSR) | Fishing harbour Blinker | #N/A | 0 | RTC X Roads( near TSR) | Fishing harbour Blinker | #N/A | 0
Dwaraka | Old Post office Blinker | Dwaraka | Dwaraka | Burma(Urvasi) | Old Post office Blinker | #N/A | 0
Burma(Urvasi) | Railway Station Out gate-Blinker | #N/A | 0 | Maddilapalem | Railway Station Out gate-Blinker | #N/A | 0
Maddilapalem | Dwaraka | #N/A | 0 | Akkayapalem | Birla | Dwaraka | Dwaraka
Akkayapalem | Birla | #N/A | 0 | Airport | Lankelapalem | #N/A | 0
Airport | Lankelapalem | #N/A | 0 | yendada | Tagarapuvalasa High way point | #N/A | 0
Vepagunta | Vepagunta | Vepagunta | Vepagunta | rama talkies | Swarnabharathi Stadium | Vepagunta | Vepagunta
yendada | Agnampudi Anjaney Swmy temple Junction | #N/A | 0 | Tenneti | Pen School | Agnampudi Anjaney Swmy temple Junction | Agnampudi Anjaney Swmy temple Junction
Agnampudi Anjaney Swmy temple Junction | Pendurthi | Agnampudi Anjaney Swmy temple Junction | Agnampudi Anjaney Swmy temple Junction | Gnanapuram | Haritha Lodge | Pendurthi | Pendurthi
Pendurthi | Tagarapuvalasa High way point | Pendurthi | Pendurthi |  | Patel junction | #N/A | 0
rama talkies | Swarnabharathi Stadium | #N/A | 0 |  | Coastal Battery | #N/A | 0
Gollapalem Junction | Gollapalem Junction | Gollapalem Junction | Gollapalem Junction |  | Tagrapuvalasa Old Bus Stand | Gollapalem Junction | Gollapalem Junction
Tenneti | Pen School | #N/A | 0 |  | Dondaparthy | #N/A | 0
Durgalamma temple | Haritha Lodge | Durgalamma temple | Durgalamma temple |  | Maharani Parlour | #N/A | 0
GVMC Gandhi Statue | Patel junction | GVMC Gandhi Statue | GVMC Gandhi Statue |  | Rushikonda | #N/A | 0
Gnanapuram | Coastal Battery | #N/A | 0 |  | Sagar nagar | #N/A | 0
| Durgalamma temple |  |  |  | Kailasagiri Top hill | Durgalamma temple | Durgalamma temple
| GVMC Gandhi Statue |  |  |  |  | GVMC Gandhi Statue | GVMC Gandhi Statue
| Tagrapuvalasa Old Bus Stand |  |  |  |  | #N/A | 0
| Dondaparthy |  |  |  |  | #N/A | 0
| Maharani Parlour |  |  |  |  | #N/A | 0
| Rushikonda |  |  |  |  | #N/A | 0
| Sagar nagar |  |  |  |  | #N/A | 0
| Kailasagiri Top hill |  |  |  |  | #N/A | 0

## BUSTOPS
BUS STOPS | COUNT | BANDWIDTH (Mbps) | LINK Provisioing for each JB | Number of Links at Junction
Hanumanthuwaka | 2 | 10 | 100MB | 1
Old Gajuwaka | 2 | 10 | 100MB | 1
Venkojipalem | 2 | 10 | 100MB | 1
Gopalapatnam petrol Bunk | 2 | 10 | 100MB | 1
kancharapalem Mettu | 2 | 10 | 100MB | 1
Collectorate | 2 | 10 | 100MB | 1
Convent | 2 | 10 | 100MB | 1
Sujataha Nagar | 2 | 10 | 100MB | 1
Madurwada bus stop | 2 | 10 | 100MB | 1
NAD | 2 | 10 | 100MB | 1
jagdamba | 2 | 10 | 100MB | 1
Gurudwara | 2 | 10 | 100MB | 1
Maddilapalem | 2 | 10 | 100MB | 1
yendada | 2 | 10 | 100MB | 1
Pendurthi | 2 | 10 | 100MB | 1
R K Beach | 2 | 10 | 100MB | 1
MVP Circle | 2 | 10 | 100MB | 1
Railway Junction | 2 | 10 | 100MB | 1
222/999 point | 2 | 10 | 100MB | 1
Anakapalli bus stn | 2 | 10 | 100MB | 1
CBS terminal | 2 | 10 | 100MB | 1
DBS in gate | 2 | 10 | 100MB | 1
Kommadi | 2 | 10 | 100MB | 1
Opp. VSP depot | 2 | 10 | 100MB | 1
Purushothamapuram | 2 | 10 | 100MB | 1
Kurmanapalem | 2 | 10 | 100MB | 1
Rama Talkies | 2 | 10 | 100MB | 1
Daba Gadens | 2 | 10 | 100MB | 1
Simhapuri Layout | 2 | 10 | 100MB | 1
Vepagunta | 2 | 10 | 100MB | 1
300

## BUS TERMINALS
BUS TERMINALS | COUNT | BANDWIDTH (Mbps) | LINK Provisioing for each JB | Number of Links at Junction
Maddilapalem | 2 | 50 | 100MB | 2
MVP Circle | 1 | 25 | 100MB | 1
Anakapalli bus stn | 1 | 25 | 100MB | 1
CBS terminal | 2 | 50 | 100MB | 2
150

## SMARTPOLES
Visakhapatnam Smart City
System Integrator Project - Smart Poles Locations
Sl no | Police Station | Name Of the Junction |  |  | Smart Poles
|  |  | X-Co ordniate | Y-Co ordinate |  | PA=5 | ECB=7 | BW in Each Locn (Mbps) | LINK Provisioing for each JB | Number of Links at Junction
1 | Arilova | Hanumanthuwaka | 83.2454 | 17.7723 | 1 |  |  | 20 | 1 GB | 1
2 | MVP | MVP Double Road | 83.3279 | 17.7428 | 1 |  |  | 20 | 1 GB | 1
3 | Gajuwaka | Old Gajuwaka | 83.2036 | 17.6851 | 1 |  |  | 20 | 1 GB | 1
4 | Gajuwaka | Sheelanagar | 83.2037 | 17.7195 | 1 |  |  | 20 | 1 GB | 1
5 | MVP | Venkojipalem Petrol Bunk | 83.0021 | 17.6861 | 1 |  |  | 20 | 1 GB | 1
6 | Gajuwaka | BHPV | 83.2056 | 17.7019 | 1 |  |  | 20 | 1 GB | 1
7 | Gopalapatnam | Gopalapatnam petrol Bunk | 83.2178 | 17.7517 | 1 |  |  | 20 | 1 GB | 1
8 | Arilova | Adarsh Nagar | 83.331 | 17.7363 | 1 |  |  | 20 | 1 GB | 1
9 | Kancharapalem | kancharapalem before gnanapuram | 83.3074 | 17.7369 | 1 |  |  | 20 | 1 GB | 1
10 | MR Peta | Collectorate | 83.3079 | 17.7083 | 1 |  |  | 20 | 1 GB | 1
11 | IV town | Diamond park | 83.3035 | 17.7269 | 1 |  |  | 20 | 1 GB | 1
12 | PM Palem | kommadi | 83.3565 | 17.8253 | 1 |  |  | 20 | 1 GB | 1
13 | I Town | Old Post office Jn | 83.2922 | 17.6936 | 1 |  |  | 20 | 1 GB | 1
14 | Airport | NAD | 83.2355 | 17.7427 | 1 |  |  | 20 | 1 GB | 1
15 | Maharani peta | jagdamba | 83.3023 | 17.7119 | 1 |  |  | 20 | 1 GB | 1
16 | II town | seven hills | 83.3094 | 17.7178 | 1 |  |  | 20 | 1 GB | 1
17 | III Town | Siripuram HSBC Junction | 83.3178 | 17.723 | 1 |  |  | 20 | 1 GB | 1
18 | III town | Maddilapalem | 83.3195 | 17.7349 | 1 | 1 | 1 | 20 | 1 GB | 1
19 | Pendurthi | Vepagunta | 83.2143 | 17.7853 | 1 | 1 | 1 | 20 | 1 GB | 1
20 | PM Palem | yendada | 83.3582 | 17.7821 | 1 | 1 |  | 20 | 1 GB | 1
21 | Pendurthi | Pendurthi | 83.205 | 17.8221 | 1 | 1 | 1 | 20 | 1 GB | 1
22 | III town | rama talkies | 83.3154 | 17.731 | 1 | 1 |  | 20 | 1 GB | 1
23 | I town | Coastal Battery | 83.3098 | 17.7055 | 1 |  | 1 | 20 | 1 GB | 1
24 | Gajuwaka | New Gajuwaka | 83.2173 | 17.6864 | 1 |  |  | 20 | 1 GB | 1
25 | PM Palem | Rushikonda | 83.3528 | 17.7914 | 1 |  | 1 | 20 | 1 GB | 1
26 | Arilova | Kailasagiri Top hill | 83.3461 | 17.7474 | 1 |  | 1 | 20 | 1 GB | 1
27 |  | Zoo | 83.3496 | 17.7483 | 1 |  |  | 20 | 1 GB | 1
28 |  | Vuda Park Beach | 83.3386 | 17.725 | 1 |  |  | 20 | 1 GB | 1
29 |  | Submiarine | 83.33 | 17.7174 | 1 |  |  | 20 | 1 GB | 1
30 |  | Bheemil Beach | 83.4556 | 17.8908 | 1 |  |  | 20 | 1 GB | 1
31 |  | GVMC Center park | 83.3067 | 17.7232 | 1 |  |  | 20 | 1 GB | 1
32 |  | Dabagaraden Saraswathi park | 83.3002 | 17.714 | 1 |  |  | 20 | 1 GB | 1
33 |  | Murali Nagar | 83.2696 | 17.738 | 1 |  |  | 20 | 1 GB | 1
34 |  | Andra University Road Peda Water | 83.3241 | 17.7266 | 1 |  |  | 20 | 1 GB | 1
35 |  | MVP Near TTD Kalyana Mandapam | 83.3346 | 17.7412 | 1 |  |  | 20 | 1 GB | 1
36 |  | MVP Circle | 83.3339 | 17.7193 | 1 |  |  | 20 | 1 GB | 1
37 |  | Stadium & Convention | 83.3033 | 17.7212 | 1 |  |  | 20 | 1 GB | 1
38 |  | Madhurwada Shilparaman | 83.3532 | 17.8049 | 1 |  |  | 20 | 1 GB | 1
39 |  | VIP Road / Sampath Vinayak | 83.3195 | 17.7203 | 1 |  |  | 20 | 1 GB | 1
40 |  | Railway Station Junction (Out gate) | 83.291 | 17.7227 | 1 |  | 1 | 20 | 1 GB | 1
41 |  | Gyanapuranm Port Circle | 83.2896 | 17.7171 | 1 |  |  | 20 | 1 GB | 1
42 |  | Urvasi Junction Polytechnic Junction | 83.2718 | 17.7347 | 1 |  |  | 20 | 1 GB | 1
43 |  | Marripalem | 83.2517 | 17.7401 | 1 |  |  | 20 | 1 GB | 1
44 |  | Seethamdhara Rythu Bazaar | 83.3135 | 17.7397 | 1 |  |  | 20 | 1 GB | 1
45 |  | Poorna Market | 83.2987 | 17.6973 | 1 |  |  | 20 | 1 GB | 1
46 |  | Simachalam Hill | 83.2484 | 17.7663 | 1 |  |  | 20 | 1 GB | 1
47 |  | Gajuwaka Gvmc Zonal Office | 83.2285 | 17.7439 | 1 |  |  | 20 | 1 GB | 1
48 |  | Steel Plant | 83.1676 | 17.6853 | 1 |  |  | 20 | 1 GB | 1
49 |  | RK Beach | 83.3181 | 17.7115 |  |  |  | 20 | 1 GB | 1
50 |  | Malikapuram |  |  | 1 |  |  | 20 | 1 GB | 1
51 |  | Scindia Junction Flyover | 83.2685 | 17.6881 | 1 |  |  | 20 | 1 GB | 1
[5 empty] | 50 |  |  | 1020

## EXISTING CAMERAS
Bandwidth details for existing cameras
For Existing cameras - only the count is available, which is 423. Detailing of the cameras per junction are required.
| S. No. | Existing cameras | Bandwith per camera (Mbps) | Total bandwith (Mbps)
| 1 | 423 | 6 | 2538

## GVSCCL-ECB FINAL LIST (hidden)
Visakhapatnam Smart City
System Integrator Project - ECB Locations
Sl no | Police Station | Name Of the Junction | ECB
1 | Gajuwaka | Old Gajuwaka | 1 | Hanumanthuwaka | Old Gajuwaka | 1 | 1
2 | Gajuwaka | Sheelanagar | 1 | MVP Double Road | Sheelanagar | 1 | 1
3 | Kancharapalem | kancharapalem Mettu | 1 | Old Gajuwaka | kancharapalem Mettu | 1 | 1
4 | IV town | ASR Statue | 1 | Sheelanagar | ASR Statue | 1 | 1
5 | I town | Collectorate | 1 | santhipuram | Collectorate | 1 | 1
6 | Harbour | Convent | 1 | Venkojipalem | #N/A | #N/A | 0
7 | II town | Pandimetta | 1 | Autonagar | Pandimetta | 1 | 1
8 | III town | Pedawaltair | 1 | BHPV | Pedawaltair | 1 | 1
9 | Pendurthi | Pinagadi | 1 | Srinagar | Pinagadi | 1 | 1
10 | Pendurthi | Chinna musidiwada | 1 | Masque | Chinna musidiwada | 1 | 1
11 | Malkapuram | Maruthi Circle | 1 | Gopalapatnam petrol Bunk | Maruthi Circle | 1 | 1
12 | Malkapuram | Scindia | 1 | Vadlapudi | Scindia | 1 | 1
13 | II town | Gokul theater junction | 1 | Adarsh Nagar | Gokul theater junction | 1 | 1
14 | New port | gangavaram port junction | 1 | ICICI Dwaraka | gangavaram port junction | 1 | 1
15 | Arilova | Visalakshi nagar NH16 | 1 | kancharapalem Mettu | Visalakshi nagar NH16 | 1 | 1
16 | PM Palem | Madhurawada ( Kommadi Junction ) | 1 | Boyapalem Jn | Madhurawada ( Kommadi Junction ) | 1 | 1
17 | I Town | Fishing harbour Blinker | 1 | Golden jubilee hospital | #N/A | #N/A | 0
18 | I Town | Old Post office Blinker | 1 | Gosala | #N/A | #N/A | 0
19 | IV Town | Railway Station Out gate-Blinker | 1 | Gopalapatnam RS Jn | #N/A | #N/A | 0
20 | Kancharapalem | Tatichetlapalem | 1 | ASR Statue | Tatichetlapalem | 1 | 1
21 | Kancharapalem | NAD | 1 | Collectorate | NAD | 1 | 1
22 | Kancharapalem | Muralinagar | 1 | Town kotha Road | Muralinagar | 1 | 1
23 | III town | Park hotel | 1 | Convent Jn | Park hotel | 1 | 1
24 | Maharani peta | jagdamba | 1 | Essar Jn | jagdamba | 1 | 1
25 | II town | seven hills | 1 | Y-Junction | seven hills | 1 | 1
26 | III town | N.T.R.circle | 1 | kapparada Jn | N.T.R.circle | 1 | 1
27 | Maharani peta | Z.P | 1 | Pandimetta | Z.P | 1 | 1
28 | II town | Ambedkar Circle | 1 | Appughar | Ambedkar Circle | 1 | 1
29 | IV town | Dwaraka | 1 | Pedawaltair | #N/A | #N/A | 0
30 | Kancharapalem | Birla | 1 | YMCA | #N/A | #N/A | 0
31 | parawada | Lankelapalem | 1 | Pandurangapuram Jn | #N/A | #N/A | 0
32 | Pendurthi | Vepagunta | 1 | Pithapuram colony | #N/A | #N/A | 0
33 | Steelplant | Agnampudi Anjaney Swmy temple Junction | 1 | Diamond park | #N/A | #N/A | 0
34 | Pendurthi | Pendurthi | 1 | Pinagadi | #N/A | #N/A | 0
35 | Bhimili | Tagarapuvalasa High way point | 1 | Sujataha Nagar | #N/A | #N/A | 0
36 | III town | Swarnabharathi Stadium | 1 | Chinna musidiwada | #N/A | #N/A | 0
37 | II town | Gollapalem Junction | 1 | Totagaruvu | #N/A | #N/A | 0
38 | II town | Pen School | 1 | Maruthi Circle | #N/A | #N/A | 0
39 | II town | Haritha Lodge | 1 | Pipe Line Junction | #N/A | #N/A | 0
40 | III town | Patel junction | 1 | Coromandel Gate | #N/A | #N/A | 0
41 | I town | Coastal Battery | 1 | Scindia | #N/A | #N/A | 0
42 | I town | Durgalamma temple | 1 | Gokul theater junction | #N/A | #N/A | 0
43 | II town | GVMC Gandhi Statue | 1 | Natayyapalem | #N/A | #N/A | 0
44 | Gajuwaka | New Gajuwaka | 1 | New Gajuwaka | New Gajuwaka | 1 | 1
45 | Bhimili | Tagrapuvalasa Old Bus Stand | 1 | Venkanna palem Port Junction | #N/A | #N/A | 0
46 | IV town | Dondaparthy | 1 | karnavanipalem Junction | #N/A | #N/A | 0
47 | IV town | Maharani Parlour | 1 | gangavaram port junction | #N/A | #N/A | 0
48 | PM Palem | Rushikonda | 1 | Hanumanthwaka Jn (Near Mekala Jn) | #N/A | #N/A | 0
49 | Arilova | Sagar nagar | 1 | Visalakshi nagar NH16 | #N/A | #N/A | 0
50 | Arilova | Kailasagiri Top hill | 1 | Visalakshi nagar Beach Road | #N/A | #N/A | 0
|  |  | 50 | Jodugullapalem | #N/A
|  |  |  | East point golf junction | #N/A
|  |  |  | Cricket Stadium Junction | #N/A
|  |  |  | Madhurawada ( Kommadi Junction ) | #N/A
|  |  |  | Krishnapuram C Jail Junction | #N/A
|  |  |  | Fishing harbour Entrance | #N/A
|  |  |  | Old Post office Jn | #N/A
|  |  |  | Victoria Statue Jn | #N/A
|  |  |  | Railway Station Out gate | #N/A
|  |  |  | Railway Station In gate | #N/A
|  |  |  | Satyam Junction | #N/A
|  |  |  | Tatichetlapalem | #N/A
|  |  |  | NAD | #N/A
|  |  |  | Kurmanapalem | #N/A
|  |  |  | Muralinagar | #N/A
|  |  |  | Dwaraka Jn | #N/A
|  |  |  | Park hotel | #N/A
|  |  |  | jagdamba | #N/A
|  |  |  | seven hills | #N/A
|  |  |  | Siripuram HSBC Junction | #N/A
|  |  |  | C.R Reddy Jn | #N/A
|  |  |  | kurupam circle | #N/A
|  |  |  | N.T.R.circle | #N/A
|  |  |  | Z.P | #N/A
|  |  |  | Asilametta | #N/A
|  |  |  | Tycoon | #N/A
|  |  |  | Gurudwara | #N/A
|  |  |  | dolphin/sea nose | #N/A
|  |  |  | Gollapalem Statue | #N/A
|  |  |  | Ambedkar Circle | #N/A

## Sheet1 (hidden)
ECB | PAS | PAS&ECB | PAS&ECB | PAS&ECB | PA |  | ECB |  | PAS PURE | ECB pure
Convent | Old Post office | Dwaraka | #N/A | 0 | #N/A | 0 | #N/A | 0 | Old Post office | Convent
Fishing harbour Blinker | RTC X Roads( near TSR) | Vepagunta | #N/A | 0 | #N/A | 0 | #N/A | 0 | RTC X Roads( near TSR) | Fishing harbour Blinker
Old Post office Blinker | Dwaraka | Agnampudi Anjaney Swmy temple Junction | Dwaraka | Dwaraka | Dwaraka | Dwaraka | #N/A | 0 | Burma(Urvasi) | Old Post office Blinker
Railway Station Out gate-Blinker | Burma(Urvasi) | Pendurthi | #N/A | 0 | #N/A | 0 | #N/A | 0 | Maddilapalem | Railway Station Out gate-Blinker
Dwaraka | Maddilapalem | Gollapalem Junction | #N/A | 0 | #N/A | 0 | Dwaraka | Dwaraka | Akkayapalem | Birla
Birla | Akkayapalem | Durgalamma temple | #N/A | 0 | #N/A | 0 | #N/A | 0 | Airport | Lankelapalem
Lankelapalem | Airport | GVMC Gandhi Statue | #N/A | 0 | #N/A | 0 | #N/A | 0 | yendada | Tagarapuvalasa High way point
Vepagunta | Vepagunta |  | Vepagunta | Vepagunta | Vepagunta | Vepagunta | Vepagunta | Vepagunta | rama talkies | Swarnabharathi Stadium
Agnampudi Anjaney Swmy temple Junction | yendada |  | #N/A | 0 | #N/A | 0 | Agnampudi Anjaney Swmy temple Junction | Agnampudi Anjaney Swmy temple Junction | Tenneti | Pen School
Pendurthi | Agnampudi Anjaney Swmy temple Junction |  | Agnampudi Anjaney Swmy temple Junction | Agnampudi Anjaney Swmy temple Junction | Agnampudi Anjaney Swmy temple Junction | Agnampudi Anjaney Swmy temple Junction | Pendurthi | Pendurthi | Gnanapuram | Haritha Lodge
Tagarapuvalasa High way point | Pendurthi |  | Pendurthi | Pendurthi | Pendurthi | Pendurthi | #N/A | 0 |  | Patel junction
Swarnabharathi Stadium | rama talkies |  | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | Coastal Battery
Gollapalem Junction | Gollapalem Junction |  | Gollapalem Junction | Gollapalem Junction | Gollapalem Junction | Gollapalem Junction | Gollapalem Junction | Gollapalem Junction |  | Tagrapuvalasa Old Bus Stand
Pen School | Tenneti |  | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | Dondaparthy
Haritha Lodge | Durgalamma temple |  | Durgalamma temple | Durgalamma temple | Durgalamma temple | Durgalamma temple | #N/A | 0 |  | Maharani Parlour
Patel junction | GVMC Gandhi Statue |  | GVMC Gandhi Statue | GVMC Gandhi Statue | GVMC Gandhi Statue | GVMC Gandhi Statue | #N/A | 0 |  | Rushikonda
Coastal Battery | Gnanapuram |  | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | Sagar nagar
Durgalamma temple |  |  | #N/A | 0 |  |  | Durgalamma temple | Durgalamma temple |  | Kailasagiri Top hill
GVMC Gandhi Statue |  |  | #N/A | 0 |  |  | GVMC Gandhi Statue | GVMC Gandhi Statue
Tagrapuvalasa Old Bus Stand |  |  | #N/A | 0 |  |  | #N/A | 0
Dondaparthy |  |  | #N/A | 0 |  |  | #N/A | 0
Maharani Parlour |  |  | #N/A | 0 |  |  | #N/A | 0
Rushikonda |  |  | #N/A | 0 |  |  | #N/A | 0
Sagar nagar |  |  | #N/A | 0 |  |  | #N/A | 0
Kailasagiri Top hill |  |  | #N/A | 0 |  |  | #N/A | 0

## GVSCCL-VMB FINAL LIST
Visakhapatnam Smart City
System Integrator Project - VMB Locations
Sl no | Police Station | Name Of the Junction | X | Y | Variable Message Board
[6 empty] | BW in Each Locn (Mbps) | LINK Provisioing for each JB | Number of Links at Junction
1 | Gajuwaka | Srinagar | 17.6837 | 83.1872 | 1 | 5 | 100MB | 1
2 | Arilova | Adarsh Nagar | 17.7638 | 83.3392 | 1 | 5 | 100MB | 1
3 | IV Town | Railway Station Out gate-Blinker | 17.7229 | 83.2909 | 1 | 5 | 100MB | 1
4 | III town | Maddilapalem | 17.7349 | 83.3197 | 1 | 5 | 100MB | 1
5 | Airport | KGH |  |  | 1 | 5 | 100MB | 1
6 | III town | Park hotel | 17.7214 | 83.3354 | 1 | 5 | 100MB | 1
7 | Kancharapalem | Airport | 17.7323 | 83.2236 | 1 | 5 | 100MB | 1
8 | Pendurthi | Vepagunta | 17.7755 | 83.2164 | 1 | 5 | 100MB | 1
9 | II town | Tenneti | 17.7125 | 83.3031 | 1 | 5 | 100MB | 1
10 |  | CR Reddy Square | 17.721 | 83.3202 | 1 | 5 | 100MB | 1
[5 empty] | 10 | 50

## Existing camera junction (hidden)
L&T survey -List of junctions with existing camera
Sl no | S.No as per main sheet | Police Station | Name Of the Junction | Lnt Proposed Cameras by considering complete junction |  | Exisitng camera
|  |  |  | Fixed | PTZ | Fixed | Mini PTZ | PTZ
1 | 1 | IV town | Asilametta | 4 | 1 | 0 | 2 | 1
2 | 2 | IV town | Dwaraka | 3 | 1 | 0 | 3 | 0
3 | 6 | IV town | Gurudwara | 3 | 1 | 0 | 2 | 1
4 | 10 | III town | Tycoon | 3 | 1 | 0 | 1 | 0
5 | 11 | Kancharapalem | Burma(Urvasi) | 5 | 1 | 0 | 2 | 0
6 | 13 | III town | Maddilapalem | 5 | 1 | 0 | 2 | 1
7 | 14 | Kancharapalem | Birla | 3 | 1 | 1 | 1 | 1
8 | 16 | Gajuwaka | 100 feet Road | 3 | 1 | 2 | 0 | 0
9 | 17 | parawada | Lankelapalem | 4 | 1 | 4 | 0 | 0
10 | 20 | IV town | Akkayapalem | 4 | 1 | 3 | 0 | 0
11 | 23 | Kancharapalem | Airport | 4 | 1 | 0 | 2 | 0
12 | 27 | Kancharapalem | Ramanna Colony | 4 | 1 | 1 | 1 | 1
13 | 28 | Pendurthi | Vepagunta | 7 | 2 | 4 | 0 | 0
14 | 30 | PM Palem | yendada | 3 | 1 | 2 | 0 | 0
15 | 32 | Steelplant | Agnampudi Anjaney Swmy temple Junction | 4 | 1 | 3 | 0 | 0
16 | 33 | Kancharapalem | Kakani Nagar | 3 | 1 | 3 | 0 | 0
17 | 34 | IV town | sangam Sarat | 4 | 2 | 1 | 1 | 0
18 | 35 | Pendurthi | Pendurthi | 5 | 1 | 4 | 0 | 0
19 | 37 | III town | Automotive | 3 | 1 | 0 | 2 | 0
20 | 38 | II town | Ambedkar Circle | 3 | 1 | 0 | 1 | 1
21 | 39 | IV town | Sri Surya | 2 | 1 | 0 | 2 | 0
22 | 41 | IV town | Rail Club(DLO) | 4 | 1 | 0 | 2 | 0
23 | 43 | Bhimili | Tagarapuvalasa High way point | 5 | 1 | 3 | 0 | 0
24 | 46 | III town | Swarnabharathi Stadium | 3 | 1 | 0 | 1 | 1
25 | 47 | Kancharapalem | Punjab hotel | 6 | 2 | 1 | 1 | 1
26 | 48 | Kancharapalem | R&B | 5 | 1 | 1 | 1 | 1
27 | 49 | II town | Sevenhills | 4 | 1 | 0 | 0 | 1
28 | 50 | III town | rama talkies | 5 | 1 | 0 | 1 | 1
29 | 51 | II town | Gollapalem Junction | 4 | 1 | 0 | 4 | 1
30 | 52 | II town | Watch house | 3 | 1 | 0 | 1 | 1
31 | 53 | II town | CPO | 3 | 1 | 0 | 2 | 1
32 | 58 | II town | Pen School | 4 | 1 | 0 | 2 | 0
33 | 59 | II town | Haritha Lodge | 3 | 1 | 1 | 2 | 0
34 | 61 | II town | Tenneti | 2 | 1 | 0 | 0 | 1
35 | 65 | III town | Patel junction | 5 | 2 | 0 | 0 | 1
36 | 66 | I town | Coastal Battery | 3 | 1 | 0 | 1 | 1
37 | 67 | I town | Durgalamma temple | 4 | 1 | 0 | 2 | 0
38 | 69 | I town | Sea Horse | 4 | 1 | 0 | 2 | 0
39 | 70 | III town | N.T.R.circle Beach | 3 | 1 | 0 | 3 | 0
40 | 71 | II town | Turner choultry | 3 | 1 | 0 | 2 | 1
41 | 72 | II town | saraswathi | 6 | 2 | 0 | 2 | 0
42 | 73 | II town | Ramakrishna | 3 | 1 | 0 | 2 | 0
43 | 74 | II town | Dolphin | 4 | 1 | 0 | 2 | 0
44 | 75 | Bhimili | Tagarapuvalasa Old Bus stand | 4 | 1 | 3 | 0 | 0
45 | 77 | II town | GVMC Gandhi Statue | 7 | 2 | 0 | 2 | 1
46 | 78 | II town | Novotel Hotel Down | 3 | 1 | 0 | 2 | 1
47 | 79 | II town | Z.P. | 4 | 1 | 0 | 2 | 0
48 | 80 | II town | Jagadamba | 4 | 1 | 0 | 1 | 1
49 | 81 | III town | Circuit House | 4 | 1 | 0 | 1 | 0
50 | 82 | III town | Siripuram | 7 | 2 | 0 | 0 | 1
51 | 84 | III town | Park hotel | 6 | 1 | 0 | 1 | 2
52 | 86 | III town | All India Radio | 7 | 2 | 0 | 1 | 1
53 | 88 | III town | Pandurangapuram down | 3 | 1 | 0 | 1 | 1
54 | 89 | III town | CR Reddy Square | 4 | 1 | 0 | 4 | 0
55 | 93 | IV town | Dondaparthy | 4 | 1 | 1 | 1 | 0
56 | 94 | IV town | Railway new colony | 4 | 2 | 1 | 2 | 0
57 | 95 | IV town | Maharani Parlour | 3 | 1 | 1 | 1 | 0
58 | 96 | IV town | Railway High School Raod junction | 4 | 1 | 0 | 2 | 0
59 | 115 | PM Palem | Rushikonda | 3 | 1 | 2 | 0 | 0
60 | 116 | Arilova | Sagar Nagar | 3 | 1 | 1 | 0 | 0
|  |  | Total | 239 | 69 | 43 | 76 | 26
Note-: L&T proposed cameras qty may changes based on the client approval

## Unidentified Junction (hidden)
L&T survey -List of unidentified junctions
S.No | Police Station | Name Of the Junction | Proposed Camera |  | Exisitng camera |  |  | Reamarks
|  |  | Fixed | PTZ | Fixed | Mini PTZ | PTZ
87 | III town | CMR Engineering College | [5 empty] | Co-ordinated with local traffic department but Location not found
108 | Kancharapalem | NAD Colony (Blinker)
110 | Gajuwaka | New Gajuwaka
122 | Arilova | Mudasarlova Rear side
126 | Arilova | Doratota

## RLVD (hidden)
RLVD junction list
S.No | Location Name
1 | Car Shed
2 | Hanumanthuwaka
3 | MVP Double Road
4 | Satyam Junction
5 | Tatichetlapalem
6 | Murali Nagar
7 | NAD
8 | Auto Nagar
9 | Gajuwaka
10 | Kurmanapalem

## Environmental sensor junction (hidden)
Environmental sensor junction provided by Pollution board
S.No | Location | Location type | Remarks
1 | Anakapalli | Commercial Area/Residential Area/Traffic Area | Location Recommended by the Zonal Commisioner Anakapalli
2 | Bhimunipatnam | Residentail Area | Location Recommended by the Zonal Commisioner Bhimunipatnam
3 | Gopalapatnam | Commercial Area/Traffic Area | Location Recommended by the Zonal Commisioner
4 | Pendurthy | Residentail Area | Location Recommended by the Zonal Commisioner
5 | Adavivaram | Residentail Area
6 | Zoo Park | Sensitive Area | Location Recommended by the Curator
7 | Sagar Nagar | Residentail Area | Location Recommended by the Zonal Commisioner
8 | Jagadamba Center | Commercial Area | Location Recommended by the Zonal Commisioner
9 | RK Beach Area | Residentail Area/Tourist Place | Location Recommended by the Zonal Commisioner
10 | Maddilapalem | Commercial Area | Location Recommended by the Zonal Commisioner
11 | Duvvada | Industrial Area | Location Recommended by the Zonal Commisioner
12 | Seethammadara | Mixed Area | Location Recommended by the Zonal Commisioner
13 | Siripuram | Traffice Area | Location Recommended by the Zonal Commisioner
14 | NAD Junction | Traffice Area | Location Recommended by the Zonal Commisioner
15 | Simhachalam Temple | Sensitive Area | Location Recommended by the EO