## RRoad
Ring Road
Tender Document Sheet
1 | Estimated Cost | 568831808 |  | 56.88 Crores
2 | Bid Period | 120 Days
3 | EMD | 1% | 5688319 | 56.88 Crores
4 | Financial TO | 2 * Estimated Cost | 1137663616 | 113.86 Crores
5 | Technical | 1 similar work Work 50% of the cost of work | 284415904 | 28.45 Crores
| Similar Work | Similar Work means construction/redevelopment of Road such as Construction of New Road, Redevelopment of existing road including widening with rigid and∕ or flexible pavement.
Sl. No | Item Description | Unit | Estimated Quantity | Per Month | Peak Construction Period of 9Months | 80% of the Estimated Quantity | Roundoff
1 | Earthwork excavation / Embankment (combined Quantities) | Cu.m | 53082 | 4423.5 | 39811.5 | 31849.2 | 31850
2 | RCC (M20,M25,M30,…..) | Cu.m | 3359.61 | 279.9675 | 2519.7075 | 2015.766 | 2020
3 | Bituminous Work/ Flexible Pavement (DBM, BC, SDBC) | Cu.m | 8582.28 | 715.19 | 6436.71 | 5149.368 | 5150
4 | Rigid Pavement/ Concrete Pavement Works (PQC ,DLC) | Cu.m | 11794.6 | 982.8833 | 8845.95 | 7076.76 | 7100
Liquid Assets
| Total duration | 12 months |  | Per Month
| Peak Construction period | 9 months | 568831808 | 63203534
| Line of Credit | 63203534 x 3 Months | 189610602 | 189610602 | 18.96 Crores
No. | Equipment Type and Characteristics | Unit | Minimum Required |  | Total
|  |  | Owned | Lease/Hired
1. | Hydraulic Excavator | Nos | 1 | 1 | 2
2. | Asphalt Paver | Nos | 1 | 1 | 2
3. | Fixed Form Or Slip Form Paver | Nos | 1 (Owned or Leased) |  | 1
4. | Vibratory Roller | Nos | 1 | 1 | 2
5. | Tippers | Nos. | 3 | 2 | 5
| Tender Capacity | A*N*1.5-B
| Estimated Cost |  | Milestones | Break up | Milestones Amt
| 568831808 | 1st | 15% at end of 3rd Month | 85324771 | 85324771 | 937635
|  | 2nd | 40 % at end of 6th Month | 227532723 | 142207952 | 1562725
|  | 3rd | 75% at end of 9th Month | 426623856 | 199091133 | 2187815
|  | 4th | 100% at end of 12th Month | 568831808 | 142207952 | 1545739
568831808